HEALTH CARE QUALITY IMPROVEMENT PROGRAM

AND

# ENABLING UNIVERSAL HEALTH COVERAGE PROGRAM

ABBREVIATIONS

ADB — Asian Development Bank
AMI — Acute Myocardial Infarction

ARMED — Armenia’s Electronic Health Information System

ATDF — Armenian Territorial Development Fund
DLI — Disbursement Linked Indicator
DLR — Disbursement Linked Result
HCF — Health Care Facility

HQIP  — Health Care Quality Improvement Program
HPIU — Health Programs Implementation Unit

IA — Implementing Agency
IVA — Independent Verification Agent

LDL — Low-Density Lipoprotein
MoH — Ministry of Health

NCDs — Non-communicable diseases
PAD — Program Appraisal Document

PDO — Program Development Objective
PforR — Program for Results

PHC — Primary Health Care

PHCCs —  Primary Health Care Centers

QI — Quality Improvement

QMCU —  Quality Management Central Unit
QOC — Quality of Care
RBL — Results Based Lending

STEMI — ST-Elevation Myocardial Infarction
UHC — Universal Health Coverage

UHI — Universal Health Insurance

WB — World Bank

Terms of Reference for the Independent Verification Agent

Validation of Results for the Disbursement-Linked Indicators

These Terms of Reference (TOR) outline the scope, objectives, and responsibilities of the Independent Verification Agent (IVA) engaged to validate the results achieved under two key health sector initiatives in Armenia: the Health Care Quality Improvement Program (HQIP) provided by the Asian Development Bank (ADB) and the Enabling Universal Health Coverage Program (UHC) provided by the International Bank for Reconstruction and Development (IBRD). Both programs are supported through results-based financing mechanisms, with disbursements tied to the achievement of specific Disbursement-Linked Indicators (DLIs) or Disbursement-Linked Results (DLRs).

- Background

The IVA shall verify the achievement of DLIs and DLRs under two results-based financing operations in the health sector of the Republic of Armenia, financed respectively by the ADB and the IBRD. Key program information is summarized below.

Table 1. Summary overview of ADB RBL (Results-Based Lending) and WB PforR (Program-for-Results) Programs

| Category | HQIP | UHC |
| --- | --- | --- |
| Financing Institution / Instrument | ADB / RBL | IBRD / PforR |
| Overall Objective / PDO (Program Development Objective)/ Outcome | To support the Government of the Republic of Armenia in expanding equitable access to quality and efficient health services, with demonstrated improvements in quality of care outcomes | To improve the quality and utilization of primary health care services, increase the efficiency of public health spending, and reduce financial barriers to accessing health services |
| Policy and Strategic Alignment | Government Development Program 2021–2026; National Healthcare Development Strategy 2023–2026; Universal Health Insurance Concept Note; Quality of Care Strategy 2022–2026; Primary Health Care Action Plan | Government Development Program 2021–2026; National Healthcare Development Strategy 2023–2026; Universal Health Insurance Concept Note; Quality of Care Strategy 2022–2026; Primary Health Care Action Plan |
| Main Results Areas / Components / Outputs | a. Climate- and gender-responsive, and inclusive health facilities for quality health services delivered; b. Capacity and organization for quality of care strengthened; c. Quality of care measurement and accountability institutionalized | a. the quality of health care improved b. efficiency of government health spending increased c. financial barriers to accessing health care reduced |
| DLIs / DLRs Subject to IVA Review | DLIs 1–7, including outcome-level and output-level DLIs covering non-communicable diseases (NCDs) management at Primary Health Care (PHC) level, Acute Myocardial Infarction (AMI) mortality reduction, health facility rehabilitation, telemedicine expansion, quality management structures and financing, availability of qualified health workers, and quality of care monitoring and reporting | Selected DLRs under DLIs 2, 3, and 6, including PHC workforce training and competence, adoption and implementation of clinical protocols, preventive PHC utilization, reduction in ACSC (Ambulatory Care Sensitive Conditions)-related hospital use, and reduction in out-of-pocket (OOP) expenditure |
| Verification Requirement | Independent verification of DLI achievement is a condition for disbursement; partial achievement and partial disbursement possible for selected DLI as defined in program implementation document (PID) | Independent verification of DLR achievement is a condition for disbursement, as defined in program appraisal document (PAD) |
| Implementation Arrangements | Ministry of Health (MoH) as executing and implementing agency (IA); Armenian Territorial Development Fund (ATDF) as IA; Health Program Implementation Unit (HPIU) responsible for coordination, reporting, and consolidation; HPIU and ATDF responsible for infrastructure-related activities; other MOH departments and agencies support implementation of particular activities as described in the PID | MoH is responsible for overall oversight and coordination; HPIU is responsible for technical and operational coordination and consolidation of verification documentation, as described in PAD |
| Program Effectiveness Date | 04 November 2025 | 30 April 2025 |
| Program Closing Date | 31 December 2028 (original) | 30 September 2029 |
| Key Legal and Program Documents | ADB Loan Agreement No. 4521; Program Implementation Document incl. Results Framework and DLI Verification Protocols | IBRD Loan Agreement No. 9709-AM; WB Program Appraisal Document, Report No. PAD 00022 (June 10, 2024); Results Framework and Verification Protocols |

Table 2. HQIP Program Disbursement-linked Indicators1

| Outcome: Quality of care improvements demonstrated |  |
| --- | --- |
| DLI 1: Control of NCDs improved at PHC level | - By 2028, the percentage of men and women with high cardiovascular risk or diabetes whose Low-Density Lipoprotein (LDL) levels are checked at least once a year increased to at least 90% |
| DLI 2: In-hospital mortality for acute myocardial infarction reduced | - By 2028, the percentage of men and women admitted with ST-Elevation Myocardial Infarction (STEMI) who received timely reperfusion therapy increased to at least 20% relative to baseline. |
| Output 1: Climate-, gender-responsive and inclusive health facilities for quality health services delivered |  |
| DLI 3: Health care facilities rehabilitated or constructed and equipped | - By 2028, at least 24 HCFs are rehabilitated or constructed and equipped, meeting criteria for climate change mitigation and adaptation, inclusive design and gender responsiveness |
| DLI 4: Health service availability through telemedicine expanded | - By 2028, telemedicine in 10 remote sites piloted and pilot evaluated with outreach activities to women, older persons and persons with disabilities |
| Output 2: Capacity and organization for quality of care strengthened |  |
| DLI 5: Institutional structure, leadership, financing and capacity for Quality of Care (QOC) activities established | - By 2025, a Quality Management Central Unit (QMCU) is operational with at least half of the members being women |
|  | - By 2025, financial resources to improve quality of care provided through the Universal Health Insurance (UHI) |
|  | - By 2028, at least 75% of HCFs have established Quality Improvement (QI) plans and at least 40% of HCFs participate actively in a socially inclusive, gender- and climate-responsive QI campaign |
| DLI 6: Availability of qualified health workers increased | - By the end of 2028, at least 60% of certified physicians and 100% of newly admitted residents are licensed according to new licensing requirements |
| Output 3: Quality of care measurement and accountability institutionalized |  |
| DLI 7: Monitoring and reporting for QOC strengthened and institutionalized | - By 2028, at least 80% of HCFs submit disaggregated data for ≥15 QOC indicators through ARMED that are visualized on dashboards |

1 The verification agent is expected to verify annual targets for the DLIs listed in Table 2 as described in the results framework and verification protocols in the Program Implementation Document.

Table 3. UHC Program Disbursement-linked Indicators

| DLI 2: Competence of nurses and family physicians in Primary Health Care Centers (PHCCs) improved based on the updated in-service training curriculum. | DLR 2.2 Year 3 Percentage of nurses and family physicians in PHC facilities have been trained based on the updated in-service curriculum DLR 2.3 Year 5 Percentage of Type 2 diabetes cases that are diagnosed and treated according to clinical protocols by PHCC providers who have completed in-service training on the updated curriculum |
| --- | --- |
| DLI 3: Inpatient care and outpatient care use in hospitals reduced for ACSCs for selected NCDs․ | DLR 3.1 Year 2 MoH has adopted clinical protocols that define care to be provided at the PHC and hospital levels for selected NCDs. DLR 3.2 Year 4 Percentage of insured population ages 35-68 that have visited a PHC facility for preventative purposes in the last 12 months DLR 3.3 Year 5 Percentage reduction is achieved inpatient and outpatient cases treated in hospitals for ACSCs for selected NCDs relative to the baseline |
| DLI 6: Share of OOP payments as a proportion of current health expenditure reduced․ | DLR 6.4 Year 5 Percentage of reduction is achieved in OOP spending of current health expenditure relative to the baseline |

Only the DLIs and DLRs explicitly listed in Tables 2 and 3 of this ToR are subject to independent verification by the IVA. For the ADB RBL the annual targets to be achieved for the DLIs listed in Table 2 are indicated in the results framework in the PID. The IVA shall be responsible for verifying and confirming the achievement of these DLIs and DLRs in accordance with the respective ADB RBL and WB PforR financing agreements, results frameworks, and verification protocols governing each program (as defined in PID and PAD), while applying a consistent and objective verification methodology across both operations. Other DLIs/DLRs under the respective programs are verified through alternative arrangements defined in the relevant program documents.

B. Scope of the Work

The main objective of the consultancy is to provide independent, timely, and credible verification and validation of the achievement of all DLIs/DLRs under the ADB RBL and selected DLRS under the WB PforR in line with the approved verification protocols and related technical requirements, including those applicable to the design, construction, rehabilitation, and equipping of health care facilities, thereby supporting evidence-based disbursement decisions, as defined in PID.

General Verification Arrangements (Applicable to ADB and WB–Supported Programs)

1. Validation of the results will be carried out by the consulting firm at the request of the MOH according to schedules agreed during the contract implementation. At the inception stage of the contract, the consulting firm will propose a robust verification methodology and validation template(s) consistent with the approved verification protocols (as defined in PID and PAD). These will be reviewed and approved by the MOH, Armenian Territorial Development Fund (ATDF), the WB and ADB.

2. The validation process may include reviewing documents provided by the MOH and ATDF, patient records, and other relevant documents and data; generating indicator data using depersonalized data from the ARMED database; interviewing key informants; conducting field visits and inspections of health care facilities; and reviewing relevant software.

3. The firm's findings and recommendations will be supported by a robust review and analysis of relevant documents and data and will include a clear rationale for the validation decision and outcome for each DLI. The validation report and all other documents prepared by the firm will be in English.

Verification of DLI 3 under the ADB RBL Operation

4. Under DLI 3 of the ADB RBL program, support is provided for the construction and equipping of 19 ambulatory care facilities as well as the construction and/or rehabilitation and equipping of four (4) polyclinics and one (1) medical / health center.

5. Verification of results under DLI 3 will be based on the applicable verification protocols and the accompanying checklist of requirements for the design and construction of health care facilities which are the part of the PID.

6. The validation of health care facilities rehabilitated or constructed and equipped to meet established criteria will be conducted in two phases:

- Phase 1 - Endorsement of the detailed architectural and engineering design and equipment list and specifications. This review shall be conducted prior to the commencement of construction works and the procurement of health care facility equipment. For subprojects where construction works have already commenced, the endorsement will be carried out retroactively at the earliest possible stage to assess compliance with the loan requirements. Where gaps are identified, appropriate justification, corrective measures, and technical guidance will be provided to ensure alignment with the loan requirements.

- Phase 2 - Construction and equipping validation. This will be conducted after the completion of the health care facility construction works and equipping of the health care facilities to validate whether the loan requirements have been met.

7. The validation phases, templates, references and requirements for DLI 3 of the ADB RBL operation will be reviewed and refined at the inception stage when the consultants will develop the verification methodology.

C. Governance, Reporting and Timelines

Reporting Structure

- The IVA shall report contractually to the MoH. Day-to-day coordination shall be carried out through the HPIU.

- For DLIs related to infrastructure rehabilitation and construction, the IVA shall coordinate technically with the ATDF, which is responsible for infrastructure implementation.

- All deliverables prepared by the IVA shall be submitted to HPIU for initial review. Following HPIU review, deliverables shall be formally endorsed by MoH and shared with the respective financing institution (ADB or WB) for acceptance, as applicable.

| Deliverable | Timeline |
| --- | --- |
| Inception report and methodology | within 4 weeks of contract signing |
| Verification methodology and templates | within 6 weeks of contract signing |
| Annual / periodic verification reports | based on DLI/DLR schedule |
| Final consolidated report | end of assignment |

Payment Schedule

| Deliverable | Payments ( from Contract Amount) |
| --- | --- |
| Inception Report (including the verification methodology and templates) | 10% |
| 34 Reports on the verification/validation of DLIs/DLRs | 85% (distributed between reports) |
| Final Summary Report | 5% |

The expected overall duration of the assignment is determined from the beginning of the contract signing until December 31, 2029, aligned with the DLI/DLR verification schedule of the programs.